## Resource Plan
Role | Name | Skill Level | FTE % | Total Hours | Hourly Rate ($) | Total Cost ($)
Project Manager | Morgan Reyes | Mid-level, generalist PM | 25% | 160 | 45 | 7200
Backend Lead | Priya Nair | Senior backend engineer | 46.88% | 300 | 55 | 16500
Mobile Lead | Jason Cole | Mid-to-senior mobile engineer | 46.88% | 300 | 50 | 15000
QA Lead | Sam Okafor | Mid-level QA engineer | 34.38% | 220 | 35 | 7700
TOTAL |  |  |  | 980 |  | 46400
Assumption: | Standard full-time hours/month used for FTE %: |  |  | 160
Project duration: 4 months (Sep-Dec 2026), matching the Section 6 project schedule. Hours and rates are planning assumptions for Release 1.0, not actuals.

## Cost Plan
Item | Category | Qty / Months | Unit Cost ($) | Duration (months) | Total ($) | Notes
Project Manager labor | Labor | 160 | 45 | — | 7200 | Morgan Reyes, 160 hrs over 4 months
Backend Lead labor | Labor | 300 | 55 | — | 16500 | Priya Nair, 300 hrs over 4 months
Mobile Lead labor | Labor | 300 | 50 | — | 15000 | Jason Cole, 300 hrs over 4 months
QA Lead labor | Labor | 220 | 35 | — | 7700 | Sam Okafor, ramps up for UAT in Nov-Dec
Cloud hosting | Infrastructure | 4 | 250 | 4 | 1000 | Backend + telemetry ingestion hosting
Third-party APIs | Infrastructure | 4 | 150 | 4 | 600 | Mapping, payment gateway, SMS verification
Licenses & dev tools | Licenses | 1 | 400 | N/A | 400 | IDE and developer tooling, one-off
Hardware / sensor prototyping | Hardware | 1 | 500 | N/A | 500 | Magnetic sensor + gateway prototypes, one-off
Subtotal |  |  |  |  | 48900
Contingency rate |  | 10% |  |  |  | 10% of subtotal, sized for a moderate-uncertainty indie project
Contingency |  |  |  |  | 4890
GRAND TOTAL |  |  |  |  | 53790

## Cashflow (Monthly)
Monthly Hours by Role
Role | Hourly Rate ($) | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Total Hours
Project Manager | 45 | 40 | 40 | 40 | 40 | 160
Backend Lead | 55 | 100 | 90 | 70 | 40 | 300
Mobile Lead | 50 | 60 | 100 | 90 | 50 | 300
QA Lead | 35 | 20 | 30 | 70 | 100 | 220
Monthly Infrastructure & One-Off Assumptions
Cloud hosting ($/month) | 250
Third-party APIs ($/month) | 150
Licenses & dev tools (one-off, Sep) | 400
Hardware / sensor prototyping (one-off, Sep) | 500
Contingency rate | 10%
Monthly Cashflow
Month | Labor ($) | Infrastructure ($) | One-Off Costs ($) | Contingency ($) | Total ($)
Sep-26 | 11000 | 400 | 900 | 1230 | 13530
Oct-26 | 12800 | 400 | 0 | 1320 | 14520
Nov-26 | 12600 | 400 | 0 | 1300 | 14300
Dec-26 | 10000 | 400 | 0 | 1040 | 11440
TOTAL | 46400 | 1600 | 900 | 4890 | 53790
Note: Backend Lead hours taper and QA Lead hours ramp up in Nov-Dec to match the QA/UAT phase of the Section 6 schedule. Totals here tie to the Cost Plan grand total.