## Gantt Chart
Task | Section | Start Week | End Week | Duration (Weeks) | Section Legend
Kickoff & Requirements (VnS/SRS) | Project Mgmt | 1 | 2.3 | 1.3 |  | Project Mgmt
WBS & Schedule Baseline | Project Mgmt | 2.4 | 3.3 | 0.9 |  | Auth & Backend
Core API & DB Schema | Auth & Backend | 3.4 | 5.1 | 1.7 |  | Mobile App
Auth (Driver/Operator/RBAC) | Auth & Backend | 4.4 | 6.3 | 1.9 |  | Web Admin Portal
Telemetry Ingestion & Live Occupancy | Auth & Backend | 5.3 | 7.3 | 2 |  | Payments
Map & Facility Search | Mobile App | 6.4 | 8.3 | 1.9 |  | QA & Release
Reservation & Checkout | Mobile App | 7.4 | 9.3 | 1.9
Digital QR Access Pass | Mobile App | 8.4 | 9.9 | 1.5
In-Garage Navigation | Mobile App | 10 | 11.4 | 1.4
Session Mgmt & Booking History | Mobile App | 10.4 | 12.3 | 1.9
Operator Dashboard & Bay Mgmt | Web Admin Portal | 7.4 | 9.4 | 2
Dynamic Pricing Engine | Web Admin Portal | 9.4 | 11 | 1.6
Reporting & Analytics | Web Admin Portal | 11 | 12.4 | 1.4
Security & Audit Console | Web Admin Portal | 11.9 | 13 | 1.1
Gateway Integration (Card/Wallets) | Payments | 8.4 | 10.3 | 1.9
PCI-DSS Compliance & Encryption | Payments | 10.3 | 11.4 | 1.1
Automated Unit/Integration Testing | QA & Release | 12.4 | 14.3 | 1.9
Load & Performance Testing | QA & Release | 14.3 | 15.3 | 1
User Acceptance Testing | QA & Release | 15 | 16 | 1
Final Delivery / Release 1.0 | QA & Release | 16.3 | 16.6 | 0.3